## Sheet1
SECP3133 HPDP Section 02
Group: 1
Project 1
Group Members |  | Matrics No
Marcus Joey Sayner |  | A22EC0193
Muhammad Luqman Hakim |  | A22EC0086
Camily Tang Jia Lei |  | A22EC0039
Goh Jing Yang |  | A22EC0052
No. | Date | Activity / Task Description | PIC | Results
1 | 16/04/2025 | First proposal documentation (Chapter 1.0) | Marcus Joey Sayner | Draft of Chapter 1 completed
2 | 22/04/2025 | First proposal submission | Marcus Joey Sayner | Proposal submitted for review
3 | 23/04/2025 | Completion of Architecture | Camily Tang Jia Lei | System architecture finalised and documented
4 | 23/04/2025 | Discussion and selection of libraries | All | Pandas, Dask, Modin, Polars selected
5 | 24/04/2025 | Discussion and changing of website for scraping | All | Target website changed from Jobstreet to MauKerja
6 | 25/04/2025 | Discussion and changing of website for scraping | All | Target website changed from MauKerja to Carlist
7 | 27/04/2025 | Report documentation (Chapter 1.0, 2.0, 3.0) | Camily Tang Jia Lei | Updated chapters to match new scraping target (Carlist)
8 | 27/04/2025 | Report documentation (Chapter 1.2) | Goh Jing Yang | Revised Attribute List
9 | 29/04/2025 | Perform crawling and scraping using requests and BeautifulSoup | Goh Jing Yang | Raw data successfully scraped using requests and BeautifulSoup
10 | 30/04/2025 | Perform crawling and scraping using urllib and BeautifulSoup | Camily Tang Jia Lei | Raw data successfully scraped using urllib and BeautifulSoup
11 | 30/04/2025 | Perform crawling and scraping using urllib and Selectolax | Muhammad Luqman Hakim | Raw data successfully scraped using urllib and Selectolax
12 | 2025-03-05 | Perform Big data processing using Pandas | Camily Tang Jia Lei | Combined all individual raw datasets into a single CSV and performed initial data cleaning using Pandas
13 | 2025-04-05 | Perform crawling and scraping using httpx and parsel | Marcus Joey Sayner | Raw data successfully scraped using httpx and Parsel
14 | 2025-05-05 | Amendment big data processing using Pandas | Camily Tang Jia Lei | Updated combine CSV code to insert data into MongoDB and read from MongoDB for further processing.
15 | 2025-05-05 | Perform Big data processing using Modin | Muhammad Luqman Hakim | Cleaned and processed dataset using Modin for performance benchmarking.
16 | 2025-06-05 | Perform Big data processing using Dask | Goh Jing Yang | Cleaned and processed dataset using Dask for performance benchmarking.
17 | 2025-08-05 | Second amendment big data processing using Pandas | Camily Tang Jia Lei | Final version of Pandas processing code completed
18 | 2025-08-05 | Second amendment big data processing using Modin | Muhammad Luqman Hakim | Final version of Modin processing code completed
19 | 2025-09-05 | Second amendment big data processing using Dask | Goh Jing Yang | Final version of Dask processing code completed
20 | 2025-12-05 | Perform Big data processing using Polars | Marcus Joey Sayner | Cleaned and processed dataset using Polars for performance benchmarking.
21 | 13/05/2025 | Complete report (Chapter 6.0) | Goh Jing Yang | Chapter 6 drafted and added to report
22 | 13/05/2025 | Complete report (Chapter 7.0, 8.0, 10.0) | Muhammad Luqman Hakim | Chapter 7, 8 and 10 drafted and added to report
23 | 14/05/2025 | Completed big data processing coding | Camily Tang Jia Lei | Code finalised and structured for all libraries, and errors fixed in Polars
24 | 15/05/2025 | Complete report (Chapter 1.0, 2.0, 3.0, 5.0, 7.0) | Camily Tang Jia Lei | Finalised chapters written and inserted into report
25 | 15/05/2025 | Amended Chapter 6.0 report | Goh Jing Yang | Revised and improved Chapter 6.0 of the report
26 | 15/05/2025 | Complete report (Chapter 4.0) | Marcus Joey Sayner | Chapter 4 completed and added
27 | 15/05/2025 | Complete report documentation | Camily Tang Jia Lei | Report formatted, labelled, and finalized
28 | 16/05/2025 | Complete slides | Camily Tang Jia Lei, Muhammad Luqman Hakim, Goh Jing Yang | Slides prepared
29 | 16/05/2025 | Documentation and final compilation | Camily Tang Jia Lei | All work compiled and zipped for submission
30 | 16/05/2025 | Github submission | Muhammad Luqman Hakim | Final version uploaded to GitHub
31 | 23/05/2025 | Report amendment | Marcus Joey Sayner | Added figure descriptions
32 | 24/05/2025 | Report amendment | Camily Tang Jia Lei | Corrected figure numbering, architecture, and explanations
33 | 25/05/2025 | Report amendment | Camily Tang Jia Lei | Moved figures/tables to appendices for clarity
34 | 25/05/2025 | Report submission | Camily Tang Jia Lei | Completed and submitted the final report document