## Sheet1
SECP3133-02
HIGH-PERFORMANCE DATA PROCESSING
ASSIGNMENT 2: MASTERING BIG DATA HANDLING
|  | Name | Matric Number
|  | Ong Yi Yan | A22EC0101
|  | Tang Yan Qing | A22EC0109
Date | Task Description |  | Group Member Responsible | Progress Status | Remarks / Notes
26/5/2025 | Finalized dataset selection from Kaggle |  | Ong Yi Yan, Tang Yan Qing | Completed | Spotify Charts dataset (3.5GB) selected
27/5/2025 | Initial data loading and inspection using Pandas |  | Ong Yi Yan, Tang Yan Qing | Completed
28/5/2025 | Apply Big Data Handling Strategies using Pandas |  | Ong Yi Yan | Completed
28/5/2025 | Apply Big Data Handling Strategies using Dask |  | Tang Yan QIng | Completed
28/5/2025 | Apply Big Data Handling Strategies using Polars |  | Ong Yi Yan | Completed
28/5/2025 | Make Comparative Analysis |  | Tang Yan Qing | Completed | Measure memory, time on different libraries
28/5/2025 | Finalize and clean big_data.ipynb notebook |  | Ong Yi Yan, Tang Yan Qing | Completed | All code blocks annotated
31/5/2025 | Complete big_data.md report writing - Dataset Selection - Comparative Analysis - Conclusion - References |  | Tang Yan Qing | Completed
31/5/2025 | Complete big_data.md report writing - Introduction - Objectives - Load and Inspect Data - Big Data Handling Strategies |  | Ong Yi Yan | Completed
2025-01-06 | Push all files to GitHub and submit |  | Ong Yi Yan, Tang Yan Qing | Completed